## Tasks
Task | Priority | Owner | Status | Start date | End date | Milestone | Deliverable | Notes
Fill in Data Tasks | Urgent | Kimberly, Sam, Steven, Allie | In progress | 2024-11-07 |  | Fill pre-made tables | Data Tables
Fill in Design Document | Urgent | Kimberly, Sam, Steven, Allie | In progress | 2024-11-06 |  | Create 1st draft of Project Roadmap | Design Document
Create Task list | None | Steven | Completed | 2024-11-06 | 2024-11-06 | Create task list | Project Tasks
Create GitHub | None | Steven | Completed | 2024-11-06 | 2024-11-06 | Create GitHub |  | https://github.com/harveysd/CSE532_Project Let me know your git hub emails and I'll add you
Check on Open AI TTS integration | Medium | Steven | In progress | 2024-11-06
Check on Open AI Image Generation integration | Medium | Kimberly | In progress | 2024-11-11
Share Colab File | High | Kimberly | Completed | 2024-11-08 | 2024-11-11 | Shared Colab File with Grooup
Map/Town Nodes | High | Steven | Not started
Town NPCs spawning | High | Allie | Completed | 2024-11-13 | 2024-11-22
Enemy NPCs spawning | High | Allie | In progress | 2024-11-15
Enemy Battles (with skill checks) | High | Allie | Not started | 2024-11-16
Character Creation During Startup | High | Sam | Not started
Game Setup | High | Sam | Not started
Save State | High | Sam | Not started